## Sheet1
BURLINGTON COUNTY BRIDGE COMMISSION PROJECT STATUS UPDATE FOR THE MARINERS' ADVISORY COMMITTEE - JUNE 12, 2019
BRIDGE | PROJECT DESCRIPTION | LOCATION(S) | PROJECT TIMELINE | WORKING DAYS AND HOURS | IMPACT TO NAVIGATION | NOTICES REQUIRED | CONTACT INFORMATION
Burlington-Bristol | Painting | Lift Span | Through September 30, 2019 | Monday through Saturday 7:30 AM to 5 PM | A reduction in the normal air draft of 135 feet by three (3) feet to 132 feet | 2 hours advance notice for all requested bridge openings | Sascha Harding, Resident Engineer (609) 923-1166
Tacony-Palmyra | Fender Repairs | Bascule Span Piers E and F | Through August 9, 2019 | Monday through Friday 7:30 AM to 3:30 PM | None | None | Sascha Harding, Resident Engineer (609) 923-1166
Tacony-Palmyra | Painting | Entire bridge | Contract Completion Date: July 4, 2020 | Monday through Saturday 7:30 AM to 5 PM except for the Bascule Span | Each waterway span is different as listed below | None | Sascha Harding, Resident Engineer (609) 923-1166
|  | PA Truss Spans | Through July 15, 2019 |  | Underdeck reduction of 4 Feet | None
|  | NJ Truss Spans | Through November 27, 2019 |  | Underdeck reduction of 4 Feet | None
|  | Arch Span | Through March 16, 2020 |  | Underdeck reduction of 3 Feet | None
|  | Bascule Span | Not scheduled yet | 24/7 during approved marine closure | Complete marine closure required; time period and exact schedule to be determined and agreed upon by MAC and then approved by USCG | None
prepared by Sascha J. Harding 061219