## Sheet1
BURLINGTON COUNTY BRIDGE COMMISSION PROJECT STATUS UPDATE FOR THE MARINERS' ADVISORY COMMITTEE - NOVMENBER 22, 2019
BRIDGE | PROJECT DESCRIPTION | LOCATION(S) | PROJECT TIMELINE | WORKING DAYS AND HOURS | IMPACT TO NAVIGATION | NOTICES REQUIRED | CONTACT INFORMATION
Tacony-Palmyra | Painting | Entire bridge | Contract Substantial Completion Date: July 4, 2020 | Monday through Saturday 7:30 AM to 5:00 PM | Each waterway span is different as listed below | None | Sascha Harding, Director of Engineering (609) 923-1166
|  | NJ Truss Spans | Through November 27, 2019 |  | Underdeck reduction of 4 Feet
|  | Arch Span | Through March 16, 2020 |  | Underdeck reduction of 3 Feet
prepared by Sascha J. Harding 112219